## Business Owners
Business Owners
https://www.scaledagileframework.com/business-owners/
Responsibilities
Prior to PI Planning
Provide input to backlog refinement
Understand and help ensure that business objectives are comprehended and agreed to by key stakeholders of the train, including the Release Train Engineer (RTE), Product Management, and System Architects
Prepare to communicate the business context, including Milestones and significant external dependencies
During PI Planning
Provide relevant elements of the business context
Are ready and available to participate in key activities, including the presentation of vision, draft plan review, assigning business value to program PI objectives, and approving final plans
Play a primary role in the draft plan review, understanding the bigger picture and how these plans, when taken together, do or do not fulfill the current business objectives
Actively circulate during planning, communicating business priorities to the teams, and maintaining agreement and alignment among the stakeholders regarding the key objectives of the train
Participate in the management review and problem-solving meeting to review and adjust scope, and compromise as necessary
Inspect & Adapt
Business Owners help assess actual value achieved versus plan, and they participate in the problem-solving workshop that follows
During PI Execution
Help validate the definition of Minimum Viable Products (MVPs) for Program Epics and guide the pivot-or-persevere decision based on delivery of the MVP
Attend the System Demo to view progress and provide feedback
Attend Agile team Iteration Planning and Iteration Retrospective meetings, as appropriate
Participate in Release Management, focusing on scope, quality, deployment options, release, and market considerations

## Epic Owner
Epic Owner
https://www.scaledagileframework.com/epic-owner/
Responsibilities
Preparing the Epic
Working with Business Stakeholders (and SMEs) to define the Epic details and supporting Lean Business Case
Working with the Development Team to size the Epic and provide input for priority action, based on Weighted Shortest Job First (WSJF)
Drive analysis of the Epic through the Portfolio Kanban to Acceptance (ready for the next PI)
Present the Lean Business Case (and supporting material) to the Lean Portfolio Management for acceptance
Define the Product Roadmap (up to 3 PIs) to guide ART priorities, working alongside the Enterprise Arch (to factor in Enabler Epics)
Implementing the Epic
Work with the Product Management Team to split the Epic into prioritzed Features
Work with the ART Team to initiate the delivery activities to realize the Business benefits from the Epic
Participate in Program Increment (PI) Planning, System Demo, and Solution Demo, whenever there is critical activity related to the epic.
Work with Agile Teams that perform research Spikes, create proofs of concept, mock-ups, etc. related to the Epic
Coordinate and synchronize Epic-related activities with Stakeholders
Understand and report on the progress of the Epic with key Stakeholders and project leadership (via Epic Dashboard)
Follow the Epic downstream through the continuous delivery pipeline and release on demand
Ownership
Portfolio Backlog (JIRA): Maintain Portfolio Kanban in JIRA from 'intake' through to 'release'
Lean Business Cases (Confluence): Maintain associated Lean Business Cases (and supporting materials) in Confluence
Epic Dashboard (Confluence): Maintain Confluence Epic Dashboard to communicate key metrics and progress for Epics
Roadmap (Confluence): Maintain the Product Roadmap on Confluence

## Enterprise Architect
Enterprise Architect
https://www.scaledagileframework.com/enterprise-architect/
Responsibility
Collaborating with Lean Portfolio Management to provide a high-level vision of enterprise solutions and development initiatives
Defining key technical initiatives that support Lean Budgets via Enabler Epics
Participating in the strategy for building and maintaining the architectural runway
Understanding and communicating Strategic Themes, and other key business drivers for architecture, to System Architects and nontechnical stakeholders
Driving architectural initiatives in the Portfolio Kanban system and participating in epic analysis where applicable
Influencing common modeling, design, and coding practices
Promoting Continuous Delivery Pipeline and DevOps capabilities
Collecting generating, and analyzing innovative ideas and technologies to use across the business
Facilitating the reuse of code, components, and proven patterns
Synchronizing the following disciplines across Solutions whenever applicable; System and data security and quality; Production infrastructure; Solution user experience (Lean UX); Scalability, performance, and other Nonfunctional Requirements (NFRs)
Ownership
Portfolio Backlog (JIRA): Maintain Enablers in the Portfolio Kanban in JIRA from 'intake' through to 'release'
Lean Business Cases (Confluence): Maintain associated Enabler Lean Business Cases (and supporting material) in Confluence
Epic Dashboard (Confluence): Maintain Architecture Dashboard to communicate key metrics and progress for Epics
Roadmap (Confluence): Maintain the Artchitecture Roadmap and communicate with the Architecture Team

## Lean Portfolio Mgmt
Lean Portfolio Mgmt
https://www.scaledagileframework.com/lean-portfolio-management/
Responsibility
Strategy & Investment Funding
Connect the portfolio to enterprise strategy: Ensuring the Portfolio strategy supports and informs TJX's broader business objectives
Fund Value Streams: Identify, fund and nurture value-streams that deliver end-user value directly or support internal business processes
Establishing Portfolio Flow: Support the Portfolio Kanban, as Portfolio business and enabler Epics are used to capture, analyze, and approve new business and technology initiatives that require collaboration of multiple value streams, or cause the formation of entirely new ones.
Agile Portfolio Operations
Coordinate value streams: Working across value streams to ensure value streams don’t build overlapping solutions that can confuse the market and dilute the return on investment as well as coordinating component strategies may support efficient reuse, minimizing total investment.
Sustain and improve: LPM has a leadership role in helping the organization relentlessly improve and achieve its business goals. This is often accomplished through a persistent Lean-Agile Center for Excellence.
Lean Governance
Forecast and budget dynamically: although traditional project cost accounting should not be required, any significant variation of spend versus plan for relatively long-lived value streams must be discussed and understood, as it may reflect a lack of alignment or a level inconsistent with the strategy.
Measure Lean portfolio performance: Each portfolio must also establish the minimum Metrics needed to assure that strategy is being implemented, spend aligns with agreed boundaries, and results are constantly improving
Coordinate continuous Compliance: No portfolio is an island unto itself. Each operates in the context of its larger environment, typically containing audit and compliance requirements. These may include internal or external financial audit, industry, and legal and/or regulatory requirements

## Product Management
Product Management
https://www.scaledagileframework.com/product-and-solution-management/
Responsibility
Understand customer needs and validate solutions: Product Management is the internal voice of the customer for the ART and works with customers (as well as Product Owners) to constantly understand and communicate their needs and participate in the validation of the proposed solutions.
Understand and support Portfolio work: Every ART lives in the context of a portfolio, so Product Management has a responsibility to understand the budget for the upcoming fiscal period, understand how Strategic Themes influence the strategic direction, and work with Epic Owners to develop the Lean business case for Epics that affect their ART.
Develop and communicate the program vision and roadmap: Product Management continuously develops and communicates the vision to the development teams and defines the features of the system. In collaboration with System and Solution Architect/Engineering, they also define and maintain the Nonfunctional Requirements (NFRs) to help ensure that the solution meets relevant standards and other system quality requirements. They are responsible for the roadmap, which illustrates, at a high level, how features are intended to be implemented over time.
Manage and prioritize the flow of work (Program Kanban): Product Management manages the flow of work through the program Kanban and into the program backlog. Product Management is responsible for making sure that there are enough features ready in the backlog at all times. For example, they have feature acceptance criteria that can be used to establish that it meets its Definition of Done (DoD). And since judicious selection and sequencing of features is the key economic driver for each ART, the backlog is reprioritized with WSJF before each Program Increment (PI) Planning session.
Participate in PI planning: During each PI planning session, Product Management presents the vision, which highlights the proposed features of the solution, along with any relevant upcoming Milestones. They also typically participate as Business Owners for the train, with the responsibility of approving PI Objectives and establishing business value.
Define releases and program increments: Owning the ‘what’ means that Product Management is largely responsible for release definition as well, including new features, architecture, and allocations for technical debt. This is accomplished through a series of Program Increments and releases, whose definition and business objectives are also determined by Product Management. Product Management works with release management, where applicable, to decide when enough value has been accrued to warrant a release to the customer.
Work with System Architect/Engineering to understand Enabler work: While Product Management is not expected to drive technological decisions, they are expected to understand the scope of the upcoming enabler work and to work with System and Solution Architect/Engineering to assist with decision-making and sequencing of the technological infrastructures that will host the new business functionality. This is typically done by establishing a capacity allocation, as described in the Program and Solution Backlogs article.
Participate in demos and Inspect and Adapt (I&A): Product Management is an active participant in biweekly System Demos, including the aggregate one at the end of the PI. They are also involved in the assessment of Metrics, including evaluation of business value achieved versus plan, and are active participants in the inspect and adapt workshop.
Build an effective Product Management/Product Owner team: Though the Product Owner and Product Management roles may report to different organizations, forming an effective extended Product Management/Product Owner team is the key to efficient and effective development. Such a team also contributes materially to the job satisfaction that comes with being part of a high-performing team, one that routinely delivers on its quality and vision commitments.
Ownership
Program Backlog (JIRA): Maintain Product Features in the Progaram Kanban in JIRA from intake through to implementation and delivery
Program Dashboard (Confluence): Maintain the Program Dashboard to communicate key metrics and progress for Features, as well as Risks/Issues
Release Schedule (JIRA & Confluence): Details of the completed Features/Stories that will be delivered to Production

## System Architect Engineer
System Architects/Engineers
https://www.scaledagileframework.com/system-and-solution-architect-engineering/
Responsibility
Participate in planning, definition, and high-level design of the solution and explore solution alternatives
Actively participate in the Continuous Exploration process as part of the Continuous Delivery Pipeline, especially with enabler Epics
Define subsystems and their interfaces, allocate responsibilities to subsystems, understand solution deployment, and communicate requirements for interactions with solution context
Establish critical NFRs at the solution level, participate in the definition of others
Operate within the Economic Framework to validate the economic impact of design decisions
Work with portfolio stakeholders, notably the Enterprise Architect, to develop, analyze, split, and realize the implementation of enabler epics
Participate in Program Increment (PI) Planning and Pre- and Post-PI Planning, System and Solution Demos, and Inspect and Adapt events
Define, explore, and support the implementation of ART and Solution Train Enablers to evolve solution intent, working directly with Agile teams to implement them
Plan and develop the Architectural Runway in support of new business Features and Capabilities
Work with Product and Solution Management to determine capacity allocation for enablement work
Support technology/engineering aspects of Program and Solution Kanbans
Provide oversight and foster Built-In Quality
Ownership
Program Backlog (JIRA): Maintain Enabler Features in the Progaram Kanban in JIRA from intake through to implementation and delivery
Program Dashboard (Confluence): Maintain the Architectual elements Program Dashboard to communicate key metrics and progress for Features, as well as Risks/Issues

## Release Train Engineer
Release Train Engineer
https://www.scaledagileframework.com/release-train-engineer-and-solution-train-engineer/
Responsibility
Manage and optimize the flow of value through the ART using various tools, such as the Program Kanban, and other information radiators. Ensuring the Tools (JIRA - Team boards, JIRA - Program Boards, Confluence) are being used and being used correctly. Ensuring the Features and User Stories are complete, accurate, have acceptance critieria etc.
Establish and communicate the annual calendars for Iterations and Program Increments (PIs)
Facilitate PI Planning readiness by fostering the preparation of Vision and Backlogs, and through Pre- and Post-PI Planning meetings. As well as Facilitate the PI planning event.
Summarize Team PI Objectives into Program PI Objectives (the RTE) and publish them for visibility and transparency
Assist tracking the execution of Epics and Features, via the Portfolio and Program dashbaords.
Facilitate periodic synchronization meetings e.g. ART sync at the Program Level
Assist with economic decision-making by facilitating feature and capability estimation by teams and the roll-up to Epics, where necessary
Coach leaders, teams, and Scrum Masters in Lean-Agile practices and mindsets
Help manage risks and dependencies and escalate and track impediments
Provide input on resourcing to address critical bottlenecks
Encourage collaboration between Teams, System Teams and Solution Architects/Engineering
Work with Product Management, Product Owners, and other stakeholders to help ensure strategy and execution alignment
Improve the flow of value through value streams using the Continuous Delivery Pipeline and DevOps
Supoprt the reporting of status to Lean Portfolio Management (LPM)
Facilitate System Demos and Solution Demos
Drive relentless improvement via Inspect and Adapt workshops; assess the agility level of the ART and Solution Train and help them improve
Foster Communities of Practice and the use of engineering and Built-In Quality practices
Develop relationships with RTEs on other ARTs to share collaeral and best practices (LACE)
Ownership
Agile Metrics (Confluence): Collation and maintenance of Agile Metrics across the PI and Teams
PI Planning: Materials, faclitations and output
Inspect & Adapt: Materials, faclitations and output
ART Sync: Plans and facilitates the ART Sync and records actions/minutes in Confluence
Risks & Issues (Confluence): Maintains all Risks/Issues in Confluence

## Product Owner
Product Owner
https://www.scaledagileframework.com/product-owner/
Responsibility
PI Planning
As a member of the extended Product Management team, the PO is heavily involved in program backlog refinement and prep for PI planning and also plays a significant role in the planning event itself. Before the planning event, the PO updates the team backlog and typically reviews and contributes to the program Vision, Roadmap, and content presentations.
During the event, the PO is involved with story definition, providing the clarifications necessary to assist the team with their story estimates and sequencing. The PO also drafts the team’s specific objectives for the upcoming PI.
Iteration Execution
Maintaining the team backlog With input from System Architect/Engineering and other stakeholders, the PO has the primary responsibility for building, editing, and maintaining the team backlog. Consisting mostly of user stories, it also includes defects and enablers. Backlog items are prioritized based on user value, time, and other team dependencies determined in the PI planning meeting and refined during the PI.
Iteration Planning The PO reviews and reprioritizes the backlog as part of the prep work for Iteration Planning, including coordination of dependencies with other POs. During the iteration planning meeting, the PO is the primary source for story detail and priorities and has the responsibility of accepting the final iteration plan.
Just-in-time story elaboration Most backlog items are elaborated into user stories for implementation. This may happen before the iteration, during iteration planning, or during the iteration. While any team member can write stories and acceptance criteria, the PO has the primary responsibility for maintaining the flow. It’s usually good to have approximately two iterations’ worth of stories ready in the team backlog at all times. More would create a queue, while less might inhibit flow.
Supporting Acceptance Test Driven Development (ATDD) – POs participate in the development of story acceptance criteria, draft them when feasible, and provide examples in support of ATDD specification by example (see the Test-First article).
Accepting stories The PO is the only team member who can accept stories as done. This includes validation that the story meets acceptance criteria and has the appropriate, persistent acceptance tests, and that it otherwise complies its Definition of Done (DoD). In so doing, the PO also assures a level of quality, focusing primarily on fitness for use.
Understand enabler work While POs are not expected to drive technological decisions, they are supposed to understand the scope of the upcoming enabler work and to collaborate with System and Solution Architect/Engineering to assist with decision-making and sequencing of the critical technological infrastructures that will host the new business functionality. This can often be best accomplished by establishing a capacity allocation, as described in the team backlog article.
Participate in team demo and retrospective As the person responsible for requirements, POs have an essential role in the team demo, reviewing and accepting stories. They also participate in the Iteration Retrospective, where the teams gather to improve their processes and are active in the Agile Release Train’s (ART’s) Inspect and Adapt (I&A) workshop.
Program Execution
Iterations and Agile teams serve a larger purpose: the frequent, reliable, and continuous release of value-added solutions. During each PI, the PO coordinates dependencies with other POs. This often occurs in weekly PO sync meetings (see the PI article for more information).
The PO also has an instrumental role in producing the System Demo for program and Value Stream stakeholders.
Inspect & Adapt
Teams address their larger impediments in the I&A workshop. There, the PO works across teams to define and implement improvement stories that will increase the velocity and quality of the program.
The PI system demo is part of the I&A workshop. The PO has an instrumental role in producing the PI system demo for program stakeholders.
To ensure that they will be able to show the most critical aspects of the solution to the stakeholders, POs also participate in the preparation of the PI system demo.
Ownership
Team Backlog (JIRA): Own the Team's backog (inherirtng Features for implementation from the Program Backlog)
Team Dashboard: Own the dashboard for the team (along with SM) to show progress and key metrics
System Demo: Responsible for running the System Demo

## Scrum Master
Scrum Master
https://www.scaledagileframework.com/scrum-master/
Responsibility
Exhibits Lean-Agile leadership Exhibits the behaviors of a Lean-Agile Leader with a Lean-Agile Mindset. Helps the team embrace SAFe Core Values, adopt and apply SAFe Principles, and implement SAFe practices.
Supports the team rules The rules of an Agile Team are lightweight, but they are rules nonetheless, and the Scrum Master is responsible for reinforcing them. These may include the rules of Scrum, Built-In Quality practices from Extreme Programming (XP), Work in Process (WIP) limits from Kanban, and any other process rules the team has agreed.
Facilitates the team’s progress toward team goals The Scrum Master is trained as a team facilitator and is continuously engaged in challenging the old norms of development to improve performance in the areas of quality, predictability, flow, and velocity. They help the team focus on daily and Iteration Goals in the context of current Program Increment (PI) Objectives.
Leads team efforts in relentless improvement Helps the team improve and take responsibility for their actions; facilitates the team retrospective. Teaches problem-solving techniques and helps the team become better problem-solvers for themselves.
Facilitates meetings Facilitates all team meetings, including (where applicable) the Daily Stand-up, Iteration Planning, Iteration Review, and Iteration Retrospective.
Supports the Product Owner The Scrum Master helps the Product Owner in their efforts to manage the backlog and guide the team while facilitating a healthy team dynamic with respect to priorities and scope.
Eliminates impediments Many blocking issues will be beyond the team’s authority or may require support from other teams. The Scrum Master actively addresses these issues so that the team can remain focused on achieving the objectives of the Iteration.
Promotes SAFe quality practices SAFe provides guidance to assist the teams in constantly improving the quality of their deliverables and meeting the Definition of Done (DoD). The Scrum Master helps foster the culture of technical discipline and craftsmanship that is the hallmark of effective Agile teams.
Builds a high-performing team Focuses on ever-improving team dynamics and performance. Helps the team manage interpersonal conflicts, challenges, and opportunities for growth. Escalates people problems to management where necessary, but only after internal team processes have failed to resolve the issue; helps individuals and teams through personnel changes.
Protects and communicates Communicates with management and outside stakeholders; helps protect the team from uncontrolled expansion of work.
Responsibilities on the train The Scrum Master helps coordinate inter-team cooperation and helps the team operate well on the train.
Coordinates with other teams The Scrum Master is typically the representative in the Scrum of Scrums (SoS) meeting, and they pass information from that meeting back to the team (see Program Increment for more details). They often coordinate with the System Team, User Experience, Architecture, and Shared Services. It is important to note, however, that the responsibility for inter-team coordination cannot be delegated entirely to the Scrum Master; every team member shares responsibility in that regard.
Facilitates preparation and readiness for ART events Assists the team in preparation for ART activities, including PI Planning, System Demos, and the Inspect and Adapt.
Supports estimating Guides the team in establishing normalized estimates and helps the team understand how to estimate Features and Capabilities.
Ownership
Team Risks/Issue & Impediments: Own risks and issues for the Team
Team Dashboard: Own the dashboard for the team (along with PO) to show progress and key metrics
Improvement Backlog: Owns the backlog and completion of team improvements
Team Meetings: Owns setup and facilitation of team meetings (Iteration Planning, Daily Stand-Up, Iteration Review, Iteration Retro, Backlog Refinement)

## Dev Team
Dev Team
https://www.scaledagileframework.com/dev-team/
Responsibility
Developer
Collaborating with the Product Owner to create and refine user stories and acceptance criteria
Committing to Team PI Objectives and Iteration plans
Estimate effort to implement User Stories
Develop Stories (as defined by the Iteration goal and priority)
Create Unit Tests to validate developed functionality
Create Automated Tests to support developed functionality
Participate in Team Events e.g. Daily Stand-Up Meeting, Iteration Planning, Iteration Reviews and Iteration Retrospectives
Identify impediments and informing the Scrum Master
Conducting research, design, prototyping and other exploration activities
Continuous improvement of the team’s process
Functional (Product Team)
Collaborating with the Product Owner to create and refine user stories and acceptance criteria
Committing to Team PI Objectives and Iteration plans
Estimate effort to implement User Stories
Working with the Product Owner to confirm that the code and acceptance tests reflect the desired functionality; writing the code
Pairing to write code and automated acceptance test cases
Support creation of Automated Tests to support developed functionality
Participate in Team Events e.g. Daily Stand-Up Meeting, Iteration Planning, Iteration Reviews and Iteration Retrospectives
Identify impediments and informing the Scrum Master
Conducting research, design, prototyping and other exploration activities
Continuous improvement of the team’s process
Ownership
Unit Tests: Own the creation and reporting of Unit Test results
Automated Tests: Own the creation and reporting of Unit Test results
JIRA updates: Ensure JIRA stories are updated on a daily basis

## System Team
System Team
https://www.scaledagileframework.com/system-team/
Responsibility
Dev Ops
Create and maintain infrastructure, including continuous integration, automated builds, and automated build verification testing
Create platforms and environments for solution demos, development, quality assurance, user acceptance testing and staging
Create products, utilities, and scripts to automate deployment
Facilitate the technical aspects of collaboration with third parties, such as data or service providers and hosting facilities
Participate in PI Planning and the Pre- and Post-PI Planning meetings and in backlog refinement to define integration and test backlog items
Test Automation
Create automated Smoke test scenarios
Support Dev Team on creation of new automated tests
Run nightly automated test against environments
System Integration
Determine and help maintain decisions and policies for appropriate branching models
Run solution-level integration scripts or manually integrate where automation is not yet possible
Assist component teams in defining inter-component interfaces
Attend other teams’ stand-ups to support daily activities
End-to-End Testing
Extend test scenarios to data sets that more closely match production
Organize test cases designed by individual teams into ordered suites
Perform manual testing and run automated tests for new features and Stories
Prioritize time-consuming tests, refactor, and run reduced test suites where applicable
Help teams create reduced-test suites that they can run independently
Performance Test
Test solution performance against Nonfunctional Requirements (NFRs) and assist System and Solution Engineering in identifying system shortfalls and bottlenecks
System and Solution Demos
At the appropriate time during every iteration, the ART demonstrates the current, whole system to stakeholders in the system demos. Likewise, the Solution Train must integrate and show progress at the solution demo. The System Team typically helps prepare the technical environments, so they adequately and reliably demo the new solution functionality.
Deployment
The System Team often has unique skills and experience related to the evolving solution. It may include senior QA personnel; perhaps the System Architect/Engineer serves as a member of this team. They have seen the solution across multiple iterations, which means they understand what it is, what it does, and how well it meets all the intended requirements. With this perspective, the System Team is likely to be directly involved in supporting the PI. As part of DevOps and the Continuous Delivery Pipeline activities, they will be doing whatever is necessary to help the ART or Solution Train prepare, package, and deploy a solution into the target environment.